## Open DA Log
DECISIONS AND ACTIONS LOG
Project Name: Renovation of St. Michael's Church to Taft Public Library | [7 empty] | Rev 33
2014-05-22
Item | Item Description | Date Requested | Responsible Person | Date Required | Status | Decision or Action | Date Delivered | Comments
56 | Contact Tim Watson to find out what type of water testing will be needed at the new site, what the expected cost will be and when it can be performed. | 2013-10-08 | Mary | 2013-10-30 | Processing | 10/30: Mary contacted Tim Watson and Joe Cronin and they decided to wait until we had the architectural firm on board so we can get their engineers involved. 11/25: Mary spoke with David Eisen of Abacus about getting their engineers involved with this as soon as possible. 12/11: Abacus/Situ will begin to investigate whether the new library needs a public water supply. 1/9/14 - Abacus is working on this with their civil engineer; we should expect an update at our next meeting with Abacus. 2/20/14 - Mary has recently spoken with David Eisen of Abacus about getting their engineers involved with this as soon as possible. Abacus/Situ will begin to investigate whether the new library needs a public water supply. 3/11/14: Fred Lapham of Shea Engineering is pursuing this for the Committee. 3/20/14: This item will be revisited once the Public Water Supply topic is resolved. 4/8/14, 4/22/14, 5/6/14, 5/12/14, 5/22/14: Nothing new to report.
101 | Obtain a quote for moisture slab testing. | 2014-03-11 | Mary | 2014-03-20 | Processing | 3/20/14: Mary mentioned that David will determine whether this is needed based on what type of flooring is recommended. Kevin and Dan stated that the church has always had moisture in the lower level. Joe stated that in his rain water report in 2013 the cupola leaked, which could have contributed to the problem. 4/8/14, 4/22/14, 5/6/14,5/12/14, 5/22/14: Nothing new to report.
102 | Explore options for someone to remove the cupola and patch the roof. | 2014-03-11 | Mary | 2014-03-20 | Processing | 3/20/14: Mary has advertised with a couple of publications seeking a taker for the cupola. Joe will also ask the Board of Selectmen if they want to offer this to the town residents. 3/26/14: Mary hadn't gotten any responses from her advertisements. 4/8/14, 4/22/14: Nothing new to report. 5/6/14: Joe mentioned that the cross on the cupola was made of wood, and that the cupola was copper. Perhaps we should consider removing the cross and shining the cupola and leaving it in place. 5/12/14: Given the tight budget, we may decide to leave the cupola after all. 5/22/14: Nothing new to report
103 | Put together bid documents for the asbestos abatement work. | 2014-03-20 | Mary | tbd | Processing | 3/26/14:The asbestos abatement work will be part of the design scope. 5/22/14: Mary suggested getting bids for abatement work in order to possibly allow the Worcester County Sherriff's dept. to perform more demo work.
106 | Complete Public Water Supply narrative and send it to Joe Cronin by the end of March. | 2014-03-26 | Fred L. | 2014-03-31 | Processing | 4/8/14: Fred updated David Eisen that he would have the work completed by mid-May. 4/22/14: Fred updated David Eisen that he would have the information to the Massachusetts Drinking Water Program by Thursday, April 24. 5/6/14: Fred spoke with Andrew on May 6 about occupancy numbers at the library to try to finalize all questions about the application, which has been submitted. 5/12/14: Fred Lapham attended the meeting and finalized all the open questions. He agreed to submit the application by 5/16/14. 5/22/14: Fred Lapham submitted the application to the DEP for a ruling on the water supply.
110 | Contact Fred Lapham to obtain a written summary of the work he has performed without compensation toward the Library Renovation project. | 2014-04-22 | Joe | 2014-05-06 | Processing | 5/6/14: Joe submitted a request to Fred regarding the work he has been performing toward the project and is awaiting his reply. 5/12/14, 5/22/14: Nothing new to report
81 | Show on the drawings where furniture could be parked when moved to allow for activities, meetings, lectures, etc. of up to 25 people | 2014-02-06 | David E. | 2014-03-06 | Open
82 | Provide alternative layouts for how furniture can be laid out for meeting functions of up to 25 people. | 2014-02-06 | David E. | 2014-03-06 | Open
83 | Review existing schedule and update it as needed. | 2014-02-06 | Mary/David E. | 2014-03-06 | Open
85 | Document what the seating capacity will be in the lower level for meeting space. It was suggested that we keep it to 25 or less due to the concerns over the public water supply requirements. | 2014-02-06 | David E. | 2014-03-06 | Open
98 | Should the water heater be a point of use system? | 2014-03-11 | Mary/David E. | 2014-03-20 | Open | 3/20/14: This will be revisited later in the project.
107 | Contact Abacus to clarify questions about the sketch for the location of the HVAC units and the MEP document. | 2014-04-08 | Mary | 2014-04-22 | Open
111 | Review the list of shelving provided by Andrew and compare it with what is shown on the 30% design. | 2014-05-06 | David E. | 2014-05-12 | Open
115 | Look into the opportunity for obtaining used shelving. | 2014-05-12 | Moritz | 2014-06-02 | Open
116 | Ensure that the cost estimate specifies a three stop, two sided elevator. | 2014-05-12 | David E. | 2014-06-02 | Open
117 | Investigate the cost of an elevator with contacts at Bay State. | 2014-05-12 | Moritz | 2014-06-02 | Open
118 | Follow up on electrical cost estimates and will validate that three phase service will be available. | 2014-05-12 | David E. | 2014-06-02 | Open
119 | Compare latest cost estimate to original budget to ensure we fully understand how hard and soft costs compare. | 2014-05-12 | Don | 2014-06-02 | Open
121 | Obtain a proposal for a structural engineer to witness test pits and write a professional engineering summary. | 2014-05-22 | Dan | 2014-06-02 | Open
122 | Inquire about getting someone to dig the test pits for a structural engineer to witness in order to determine if footings exist under the foundation of the building. | 2014-05-22 | Susan | 2014-06-02 | Open
123 | Ask Abacus if they would be willing to move forward with the project assuming that no footings exist. | 2014-05-22 | Mary | 2014-06-02 | Open
1 | Post pictures from St. Michael's Church so others can view. | 2013-01-16 | Bill | 2013-01-23 | Closed | Pictures have been posted to Google Photo Site for all to see. Link is attached in comments to the right. | 2013-01-18 | Link to pictures of St. Michael's Church
2 | Title V Inspection | 2013-01-16 | Susan / Kevin | 2013-01-30 | Closed | Title V Inspection was not performed. Item was removed from P&S Agreement by Town Counsel. As built drawings for septic system are on file in Board of Health office at Town Hall. The system was built in 2009, so expectations are that it is in good condition. | 2013-01-30 | 1/30: Need to understand if change from church to library alters the requirements of the septic system. Will generate a new action in the log for this.
3 | Review Mass Building Code requirements to understand impact of going from a church (A4) to a library (A3). | 2013-01-16 | Moritz | 2013-02-27 | Closed | 6/6: Moritz has gathered information regarding what we believe is needed to bring the new library building into compliance with Mass Building Code. The information will be kept for future review after the architect is brought on board. 2/20/14: Abacus informed the Committee that the church was the same code as the library (A3), so this is no longer a concern. | 2014-02-20 | 2/27: Moritz reported that he is still investigating this and will bring a comprehensive update to the March 13 meeting. 3/20: Moritz provided an update on the need for a sprinkler system and a 2000 gallon septic system. Moritz will try to get copies of the septic system plans and the well water specifications from the Board of Health. 6/26: Kevin Rudden picked up the septic plans and provided them to Don for future reference.
4 | Get someone to clear snow from walk and steps at St. Michael's Church. | 2013-01-16 | Kevin | 2013-01-30 | Closed | Tim Hoar will clear snow if accumulation is more than 3 inches. Boy Scout will clear snow if less than 3 inches. | 2013-01-30 | 2/13: Kevin will get name of scout responsible to Andrew so he can coordinate.
5 | Find out what it will take to get natural gas to the church property. | 2013-01-23 | Paul / Jay | 2013-02-27 | Closed | 5/23: Paul updated the group that NSTAR has completed the survey and the estimate to bring the gas main/service to the new Mendon library at 29 North Avenue would cost ~$52K. This information will be kept on record for review after we have the architect on board. | 2013-05-23 | 1/30: Clough was hooked up at no cost to the town. Paul spoke with Marjorie McDonald from NStar and she is evaluating what it will take now. 2/13 update: M. McDonald called Paul earlier today and left a msg. Paul will return the call. 2/27: Paul brought non-binding applications to inquire about cost for a main line and a hookup to the new library. Joe/Don will take these to the BOS for review. 3/20: Don and Joe took the request to the BOS for signature and Joe forwarded the signed forms to NStar. Now awaiting a response. 3/27: Still awaiting a response from NStar. 4/10: NStar is working on the quote; we should hear back soon.
6 | Test Fire Alarm System once phone is set up at the church. 5/13: What will monitoring cost? (Paul) 5/13: What do the schools pay for their service? (Don) 5/13: What does the town pay for monitoring service for other buildings? (Kevin) | 2013-01-30 | Paul | 2013-02-27 | Closed | 3/27: Mike Ammendolia informed the committee that we can hook directly to Mendon Dispatch. Paul contacted Lawney Tinio to make this happen, and has since met with Custom Alarm. Stil have many questions to answer. 5/23: Paul updated the group that he had been in contact with the Mendon Fire Deparment and Custom Alarms and that it would cost ~$400/year to add monitoring to the existing alarm system. The group will not act on this at this time. Joe was in contact with the insurance company and while it is better to have the monitoring in place, having the alarm sound with no monitoring is bettet than nothing. 5/30: Don updated the group that he got in touch with Jay Byer and the cost for the schools to monitor their buildings is $650/year each. Jay also informed Don that the two schools in Upton are connected directly to Upton Dispatch, so no monitoring fee is required. He said that Mendon has a grant to upgrade its dispatch center after which time the schools might be able to dial in directly. Jay will update Don when he learns more. | 2013-05-23 | 2/13: Fire Alarm works fine but it requires the dialer to go to a third party monitoring company. Paul will check to see what it would take to make this a direct line to the Mendon Dispatch Center. 2/27: Group agreed to take this issue to the BOS to see if a direct connection to Mendon Dispatch is possible. 3/20: Don and Joe asked the BOS if they could find out if the new library could tie directly into Mendon Dispatch. The committee is awaiting an answer. 4/10: Paul has been in contact with Lawney Tinio and Lawney believes that the fire alarm system in the former rectory can be added to the existing service currently used for the Town Hall. Paul will set up an appointment to get the system set up and tested during the next week. 5/13: Paul met with Custom Alarms and is working out a possible solution. Many questions need to be answered, can the panel be reprogrammed? Do we need a second phone line? What type of monitoring does our insurance require? How much will monitoring cost? Where will the funds come from?
7 | Gather simpler RFQ's for OPM's for review at 2/13 meeting. | 2013-01-30 | Amy / Kevin | 2013-02-13 | Closed | Marshfield Fire Station document was reviewed on 2/13. Joe Cronin took action to revise this document for the rest of the committee to review on 2/27. | 2013-02-13 | 2/13: Amy provided Request for Designer Services from the construction of a Fire Station in Marshfield.
8 | Log in to new town email so we can all use these for future correspondences. | 2013-02-13 | Full Committee | 2013-02-27 | Closed | 3/27: All committee members can now access their town email accounts so we will use them for all future business pertaining to the building committee. | 2013-03-27 | 2/27: Some have had issues with this. They will seek tech support from JNiro@Worldband.com. 3/20: A couple of members are still having problems logging in. Everyone agreed to take care of this.
9 | Edit the Marshfield Fire Station request for services for OPM and send to committee for review at 2/27 meeting. | 2013-02-13 | Joe | 2013-02-19 | Closed | Joe completed the updates and distributed the document to the full team for review. | 2013-02-19
10 | Once members receive OPM document, send comments to Don so he can compile for review at 2/27 meeting. | 2013-02-13 | Full Committee | 2013-02-25 | Closed | A few members provided updates to Don, which he compiled and distributed to the committee at the 2/27 meeting. | 2013-02-25
11 | Check with Anne Mazar to understand what Fuel Efficient Vehicles Policy, Criteria 4 means and if Mendon has adopted it. | 2013-02-13 | Kevin | 2013-02-27 | Closed | No action needed. | 2013-04-10 | 4/10: Kevin provided Don with a copy of a document that explains Criteria 4 of the Green Communities Program. Essentially it is something that the Selectmen have to keep updated annually. The Building Committee does not have to be concerned with it.
12 | Check with Linda Hawkes and Claudia Cataldo to understand requirements and timeline to obtain funding for project. 5/13: Send updated timeline of funding needs to Linda. (Susan) | 2013-02-13 | Susan | tbd | Closed | 5/23: Susan sent the updated timeline of funding to Linda Hawkes and Linda will set up a bond schedule making funds available in FY14. | 2013-05-23 | 2/27: Susan stated that we were getting close to gaining access to money, but we needed to forecast how much money we needed to spend and when so we don’t borrow too much up front. Joe suggested a payment schedule for the OPM of 25% when we get the architect, 25% after the drawings were received, and 50% during the construction work phase. Dan suggested even less up front, and Joe stated we may just have a flat monthly payment plan over the course of the project. Nothing was agreed yet, but Susan stated that she has enough information for Linda to get the funding started. 5/13: Joe created a timeline for funding needed. Susan will provide this to Linda Hawkes.
13 | Gather sample RFQ's for architect for review at future meeting. | 2013-02-13 | Amy | 2013-03-20 | Closed | 3/20: Amy provided sample RFS documents to the committee for review at a future meeting. | 2013-03-20
14 | Request time on next BOS meeting to discussion natural gas and direct line to Mendon Dispatch for alarm system. | 2013-02-27 | Don | 2013-02-28 | Closed | 3/20: Don sent the request and Joe and Don were put on the agenda for the March 4th BOS meeting. | 2013-02-28
15 | Update OPM RFS document with committee inputs and send to Joe, Amy and Sue for review prior to town counsel. | 2013-02-27 | Don | 2013-03-03 | Closed | 3/20: Don compiled inputs from the committee and provided it to Susan for Town Counsel review. | 2013-03-02
16 | Bring natural gas and alarm system direct line requests to BOS at their next meeting. | 2013-02-27 | Joe / Don | 2013-03-04 | Closed | 3/20: Joe and Don took the requests to the BOS on March 4th. | 2013-03-04
17 | Send updated OPM RFS document to Legal Counsel after revisions by Don, Joe and Amy are incorporated. | 2013-02-27 | Susan | 2013-03-08 | Closed | 3/20: Susan provided the document to Town Counsel and inputs were received. The committee reviewed the comments at the 3/20 meeting. | 2013-03-15
18 | Obtain copies of the septic system plans and well specifications from the Board of Health. | 2013-03-20 | Moritz Kevin | 2013-04-03 | Closed | 6/26: Kevin provided copies of the septic system plans to the Committee. Don is holding them with other Library Committee documents. | 2013-06-26 | 4/24: Moritz has not had a chance to pick up the plans. Kevin Rudden offered to do this for Moritz. 5/13: Kevin hasn't had a chance to get the documents yet. 5/23: Kevin has the septic plans, but was unable to attend on 5/23 so he'll bring them to the next meeting.
19 | Follow up on available shelving at U Mass Dartmouth. | 2013-03-20 | Andrew Joe | 2013-04-03 | Closed | 3/27: Building Committee agreed to take the shelving for potential future use. Joe contacted Lawney Tinio and he has obtained the shelving. It needs to be moved to the old Fire Station for storage. 5/30: Joe, Moritz and Paul will put some shelving together on June 5th at the future home of the library. It is believed that the shelving is too heavy to have the boy scouts unload it, so the group will discuss what to do after Joe, Moritz and Paul experiment with moving some of the shelving. 6/18: There has been no update as to when the shelving needs to be loaded into the old Fire Station. 7/31: Shelving needs to be removed from the trailers. Paul will work with Moritz to determine if the shelving is useful to the project (see item #34 below). Pending outcome of that action, decision will be made whether to store shelving in the garage behind the old rectory at the project site or recommend that the material be scrapped. 8/14: Moritz was unable to obtain documentation for assembling the shelving, and the Super from the project is no longer at Consigli. Given the current condition of the materials, the Committee will recommend to Lawney TInio that he try to sell the material to recoup his costs for storage. Don will ask Joe to cotact Lawney about this. 8/21: Don informed the Committee that Joe Cronin has contacted Lawney Tinio to inform him of the Committee’s decision not to use the shelving due to its condition. Lawney will take care of the shelving from here. | 2013-08-21 | 4/10: Lawney Tinio has arranged to have the donated shelving stored at the old Fire Station. It will be delivered on Saturday, April 20th. 4/24: U Mass Dartmouth was closed on 4/20, so the shelving will now be delivered on May 4th. 5/13: Shelving was picked up by Tinio Corp. It now needs to be moved from trailers to the old Fire Station for storage. 5/23: Joe suggested that we take some pieces to 29 North Avenue to put them together and understand how much will be needed and where it can be used. Joe will look into getting some pieces over to the church.
20 | Send updated OPM RFS document to Legal Counsel for final review/approval. | 2013-03-27 | Susan | 2013-04-03 | Closed | 4/10: Susan took care of this and the document will get its final review at the 4/10 meeting. | 2013-04-03
21 | Contact Diane Willoughby to determine process to advertise for OPM services in the Milford Daily News. | 2013-03-27 | Don | 2013-04-08 | Closed | 4/10: Don contacted Diane and has the information needed to advertise in the Milford paper. A fee will be charged for this advertisement. | 2013-04-08
22 | Contact proper personnel at Dodge Report to determine what is needed to advertise for OPM services. | 2013-03-27 | Joe | 2013-04-08 | Closed | 4/10: Joe contacted the appropriate personnel and knows what is needed to advertise in the Dodge Report. There is no fee. We will also submit the advertisement to the Central Register. | 2013-04-08
23 | Review OPM Contract received from Town Counsel as well as fire station contract in preparation for discussion at April 10th meeting. | 2013-03-27 | Full Committee | 2013-04-10 | Closed | 4/10: The OPM Contract will be reviewed by the committee at the 4/10 and 4/24 meetings. | 2013-04-10
24 | Create first draft of RFS for Architectural services using town of Granby document as a reference. | 2013-03-27 | Joe | 2013-04-08 | Closed | Committee will review the RFS for Architectural Services at a future meeting in preparation of reviewing it with the OPM once we have one on board. | 2013-05-13 | 4/10: Joe needs to do a bit more work to complete the first draft. The Committee will review this at a future meeting. 5/13: Joe completed the first draft of the document. The Committee will review it at a future meeting.
25 | Add parking lot lighting and outdoor mounted equipment to future action items list of Decision Action Log | 2013-03-27 | Don | 2013-04-10 | Closed | 4/10: Don added these two items to the Potential Future Action Items tab of the Decision Action Log workbook. | 2013-04-10
26 | Contact Blythe Robinson in Upton to obtain copies of their RFS for an Architect for the Town Hall Renovation project. | 2013-04-10 | Kevin | 2013-04-24 | Closed | 4/24: Kevin obtained the sample documents from Blythe Robinson and sent them to Don. Don forwarded them to Joe for him to use on the first draft of our architectural services RFS. | 2013-04-24
27 | Update OPM Contract by replacing RFQ with RFS and St. Michael's Church with 29 North Avenue throughout the document | 2013-04-24 | Don | 2013-05-13 | Closed | 5/13: Committee will use the updated contract once the OPM is selected. | 2013-05-13 | 5/13: Don updated the document and distributed it to the Committee for further review and input.
28 | Invite Rich Schofield to the 5/13 meeting to discuss funding for short term needs. | 2013-05-13 | Joe | 2013-05-23 | Closed | 5/30: Joe invited Rich to the 5/23 and 5/30 meeting but Rich was unable to attend either. This will be revisited in the future. | 2013-05-30 | 5/23: Joe invited Rich but he was unable to attend. Joe will ask Rich to attend the next meeting on 5/30.
29 | Attend Mendon BOS meeting on 5/21 and bring the following items to them: lawn cutting at 29 North Avenue, insurance on 29 North Ave and requirement for fire alarm monitoring, possible sale and relocation of rectory, and short term payment of bills (e.g. $110 for ad in Milford Daily News). | 2013-05-13 | Joe/Susan | 2013-05-21 | Closed | 5/23: . Joe and Susan attended the Mendon BOS meeting on 5/21 and the BOS appointed the committee to additional terms to extend through the life of the project, they named Mark Reil as their liaison to the building committee, they will look into getting the lawn cut at the new property and they will look into getting the police to use the rectory as office space in lieu of renting trailers in the center of town. | 2013-05-23
30 | Check with Claudia about possibility of paying short term bills with Taft Library funds and get reimbursed from bond at a later time. | 2013-05-13 | Andrew | 2013-05-23 | Closed | 5/23: Andrew confirmed with Claudia that paying short term bills with state aid and getting reimbursed with bone money later is okay. | 2013-05-23
31 | Check with DOR about possibility of paying bills with short term expense funds and getting reimbursed with bond funds from debt exclusion in the future. | 2013-05-13 | Susan | 2013-05-23 | Closed | 5/23: There was no need to do this separately as Claudia looked into this for the committee. | 2013-05-23
32 | Send updated rating sheet with appropriate weights to the full Committee after the May 30 meeting. | 2013-05-30 | Don | 2013-05-30 | Closed | 6/6: Don sent the score sheets to the Committee on May 30 as planned. | 2013-05-30
33 | Send completed score sheets to Don prior to the June 6 meeting. | 2013-05-30 | Full Committee | 2013-06-06 | Closed | 6/6: Nine of the ten Committee members submitted their score sheets to Don on time. | 2013-06-06
34 | Take some shelving from Morrison Drive to the future site of the library to set it up and learn how it fits together, how much space it takes, etc. | 2013-05-30 | Joe, Moritz, Paul | 2013-06-05 | Closed | 7/31: Paul, Joe and Moritz tried to put the shelving together but there are many pieces, including buckets of bolts and nuts. They were not able to figure out how to assemble the shelves. Moritz will be checking with Consigli and U Mass Dartmouth to try to find someone who knows how to put the shelving together. He will also try to identify the manufacturer to try to get assembly instructions. If we are unable to determine how to assemble the shelving, we will recommend to Selectman Tinio that we are not interested in using the material. The group hopes to decide on this by the next meeting on August 14th. 8/14: Moritz was unable to obtain documentation for assembling the shelving, and the Super from the project is no longer at Consigli. Given the current condition of the materials, the Committee will recommend to Lawney TInio that he try to sell the material to recoup his costs for storage. | 2013-08-14 | 6/6: Joe, Paul and Moritz took some pieces to 29 North Avenue on June 5th to put them together and understand how much will be needed and where it can be used. Unfortunately, they didn’t have all the right pieces, so they will meet again on June 11th at 6:30pm at Morrison Drive to get more shelving pieces and to do more work. 6/18: The group got rained out on June 11th. They will try again in the future.
35 | Contact Diane Willoughby to request that LPA be invited to an interview on June 18th at 7:30pm at the Mendon Town Hall. He will also provide Diane with a statement to send to the other four firms regarding the status of the OPM selection process. | 2013-06-06 | Joe | 2013-06-10 | Closed | 6/18: The inteview will take place on June 26th as the OPM wasn't available on the 18th. | 2013-06-10
36 | Ask Kevin to look into ADA requirements for public libraries in order to educate the Committee. | 2013-06-06 | Joe | 2013-06-28 | Closed | 6/18: Kevin verified that the spacing for shelving should be 42". | 2013-06-18
37 | Add Judy Leonelli’s name to the volunteer donation tracking sheet and will work with Andrew and or Bill McHenry to have the list posted to the renovation website. | 2013-06-06 | Don | 2013-06-28 | Closed | 6/18: Don added Judy Leonelli’s name to the donation tracking sheet. Joe suggested we also add the names of those who volunteered to cut the lawn at the church: Jay Washburn (once) and Mike Watson (twice). Don agreed to do this as well. Susan contacted a landscaper and estimated that this has saved the committee ~$50 per mowing. 6/28: Don added all the requested items to the Donation List. | 2013-06-28
38 | All members of the Building Committee need to get sworn in for the new fiscal year beginning July 1, 2013. | 2013-06-18 | Full Committee | 2013-07-01 | Closed | 7/31: All members have been sworn in for FY 14. | 2013-07-31
39 | Arrange to meet with BOS on 7/15 to recommend going into negotiations with LPA for OPM services. | 2013-07-02 | Joe | 2013-07-08 | Closed | 7/31: Paul, Susan and Don met with BOS on 7/15 to recommend that the Town negotiate with LPA for OPM services. Contract negotiations are nearly complete at this time. | 2013-07-31
40 | Request OPM for a plan on how they can assist with the process of selecting an architect. | 2013-07-02 | Full Committee | 2013-07-30 | Closed | 7/31: Paul will contact Mary Bulso from LPA to inquire about support for completing the RFP for Designer Services. 8/14: Mary was unable to attend the 7/31 meeting, but is planning on attending the meeting on 8/14. | 2013-08-14
41 | Update the RFS for Designer Services and to provide it to Paul for submission to the OPM for review, along with the document from the Town of Weston. | 2013-07-31 | Don / Paul | 2013-08-07 | Closed | 8/14: Don updated the RFS document and provided it to Paul, who supplied it to Mary Bulso, OPM, along with other pertinent documents. | 2013-08-14
42 | Put together a request to meet with the CPC to discuss opportunities for CPA funding in the near future, perhaps in the September timeframe, and bring a proposal to the next meeting. | 2013-07-31 | Kevin | 2013-08-14 | Closed | 8/14: Kevin provided a document that the Committee reviewed and approved for release at its meeting on 8/14. | 2013-08-14
43 | Redact social security numbers, driver’s license numbers, and bank/financial account numbers from the written proposals for future review by P3 Project Planning Professionals. | 2013-07-31 | Kevin | 2013-08-14 | Closed | 8/14: Kevin redacted all the confidential information he found in the OPM proposals. The Committee will now make them available to P3 for review. | 2013-08-14
44 | Let Diane Willoughby know that we will have the documents ready for P3 to review after our next meeting, which will be scheduled for August 14th. | 2013-07-31 | Don | 2013-08-01 | Closed | 8/14: Don informed Diane Willoughby about the availability of the redacted documents so she can alert P3 of their availability date. | 2013-08-14
45 | Contact Joe and Paul to determine how to work with Diane Willoughby to arrange for a meeting with P3 to review the redacted bids received for the OPM position. | 2013-08-14 | Don | 2013-08-21 | Closed | 8/21: Don informed the Committee that he has been in contact with Joe, Paul and Diane and that Joe will work with P3 to arrange a day/time to review the redacted bids for the OPM position. | 2013-08-21
46 | Contact Joe and Paul to ask one of them to get in contact with the CPC to discuss the opportunity for CPA funding using the statement provided above. | 2013-08-14 | Don | 2013-08-21 | Closed | 8/21: Susan informed the group that the Taft Library Trustees had met with the CPC and Historical Commission in the past when they were considering purchasing the church property. The Historical Commission voted that the church building would not be eligible for CPA funding but that the existing Taft Library would. There was no discussion on the rectory, but Susan felt we should wait to determine the future plans for the rectory until after we work with the architect on the adaptive reuse of the former church. At that time we will have a clearer picture of the plans for the rectory and can pursue funding if it makes sense. | 2013-08-21
47 | Contact Diane Willoughby to schedule a review of redacted OPM bids with P3. | 2013-08-21 | Joe/Paul | 2013-09-06 | Closed | 10/8/2013: Diane and Joe have tried to contact P3 without success, so this item will be dropped. | 2013-10-08 | 8/27: Don reported that Joe has been in contact with Diane Willoughby to set up time with P3. Still working on agreeing on a day/time to meet.
48 | Provide list of all Building Committee member emails to OPM. | 2013-08-21 | Don | 2013-08-23 | Closed | 8/27: Don sent the email list to Mary. | 2013-08-23
49 | Update RFP for Designer Services and provide updated version to full Committee for review at next meeting. | 2013-08-27 | Don/Mary | 2013-09-05 | Closed | 9/5/2013: Don distributed the updated RFP to the Committee for review at the 9/5 meeting. | 2013-09-05
50 | Submit advertisement for RFQ for Designer Services to the Central Register and Dodge Report. | 2013-09-16 | Amy | 2013-09-17 | Closed | 9/19: Amy submitted the advertisement to the Central Register and Dodge Report for posting on 9/25/13. | 2013-09-17
51 | Submit advertisement for RFQ for Designer Services to the Milford Daily News. | 2013-09-16 | Don | 2013-09-17 | Closed | 9/19: Don submitted the advertisement to the Milford Daily News for posting on 9/25/13. | 2013-09-17
52 | Update RFQ for Designer Services and distribute to Committee for one last reading to ensure all updates were captured. | 2013-09-19 | Don | 2013-09-25 | Closed | 10/8: Don distributed the updated RFQ to the full Committee for review. | 2013-09-25
53 | Compile responses to questions from potential responders and send to Don for posting to the library website. | 2013-10-08 | Joe | 2013-10-15 | Closed | 10/24: Addendum containing questions from potential responders was posted on 10/15. | 2013-10-15
54 | Update matrix to be used for rating and ranking the responders to the RFQ for Designer Services. | 2013-10-08 | Don | 2013-10-24 | Closed | 10/24: Don distributed the updated rating matrix that will be used to rate the three responders to the RFQ for Deisgner Services. | 2013-10-24
55 | Send a letter to Library Trustees to explain the contribution of $10,000 as a matching grant for donations to the Taft Library Building Renovation project. | 2013-10-08 | Kevin | 2013-10-24 | Closed | 10/24: Kevin sent a letter to the Taft Library Trustees regarding his challenge donation. Susan Darnell sent a thank you letter on behalf of the trustees to Kevin. | 2013-10-24
57 | Drop sign-in sheet from site visit for potential responders to RFQ for Designer Services off at Town Hall. | 2013-10-08 | Paul | 2013-10-21 | Closed | 10/24: Paul dropped off a copy of the sign-in sheet from the site visit for potential responders to the RFQ for Designer Services to Diane Willoughby at the Town Hall. | 2013-10-24
58 | Provide updated drawings to Joe to be scanned and posted to library website. | 2013-10-24 | Mary | 2013-10-30 | Closed | 11/5: Mary provided the drawings to Joe and he sent them to Andrew to have them posted to the library website, which he did. | 2013-11-05
59 | Perform reference checks for Abacus/Situ. | 2013-10-30 | Amy | 2013-11-05 | Closed | 11/5: Amy performed the reference checks on Abacus/Situ and presented her findings to the full Committee at the 11/5 meeting. | 2013-11-05
60 | Perform reference checks for DRA. | 2013-10-30 | Paul | 2013-11-07 | Closed | 11/7: Paul performed the reference checks on DRA and presented his findings to the full Committee at the 11/7 meeting. | 2013-11-07
61 | Contact Diane Willoughby to be put on the agenda of an upcoming Board of Selectmen’s meeting to present the recommendation of Abacus/Situ as the selected design firm. | 2013-11-07 | Joe | 2013-11-18 | Closed | 11/20: Abacus was not available on 11/18 so they will be on the Board of Selectmen's agenda on 12/2 instead. | 2013-11-14
62 | Contact all three responders to the RFQ for Designer Services to inform them of the Building Committee's decision. | 2013-11-07 | Mary | 2013-11-08 | Closed | 11/9: Mary called all three responders to notify them of the Building Committee's decision. Formal letters will be sent to the three responders after approval from the Mendon BOS to enter into contract negotiations with the selected firm. 12/11: Mary contacted all three responders to inform them of the decision. | 2013-12-11
63 | Contact Arcudi Oil to inform them not to deliver oil to the future site of the public library this winter. | 2013-11-07 | Andrew | 2013-11-15 | Closed | 12/11: Andrew has contacted Arcudi Oil to stop delivery of oil to 29 North Avenue. | 2013-12-11
64 | RSVP to Lisa Lepore if you want to attend the Employee and Volunteer Holiday Party. | 2013-11-20 | Full Committee | 2013-12-01 | Closed | 12/11: A few members of the Building Committee plan to attend the Employee and Volunteer Holiday Party. | 2013-12-11
65 | Ask Building Inspector if a variance will be needed for the new library building for lack of distance to center of street . | 2013-11-20 | Kevin | 2013-12-11 | Closed | 12/11: Kevin spoke with Tim Aicardi who doesn't think that a variance is needed but needs to investigate further to be certain. Pre-existing buildings do not need the variance, but the change of use may change this. Kevin will follow up with Tim on this and update the Committee at the next meeting. 1/9: Kevin spoke to both Mendon’s Building Commissioner, Tim Aicardi, and Milford’s (John Erickson, whom Tim works for part-time) regarding the question of whether a zoning variance or special permit is needed in order to convert the former St. Michael’s Church building into a new town-owned library building. Aicardi and Erickson reviewed Mendon’s zoning by-laws together and told Kevin that a variance/special permit is not needed. 2/20/14 - Kevin received an update from Tim Aicardi (Mendon Building Inspector) that a variance is not needed. We have this in writing, so this item is now closed. | 2014-02-20
66 | Send Building Committee contact information to Abacus/Situ. | 2013-12-11 | Don | 2013-12-13 | Closed | 1/9: Don sent the Building Committee contact information to Abacus/Situ the day after the last meeting.
66 | Contact Mary and Abacus/Situ to ask if they can meet at the new site on 12/10 or 12/11. | 2013-11-20 | Joe | 2013-12-03 | Closed | 11/26: Joe contacted Mary Bulso who contacted Abacus/Situ about meeting at the future site of the Taft Public Library for our next meeting. Everyone is available to do this on Wednesday, December 11th. Don has posted a meeting for that date. | 2013-11-25
67 | Contact Anne to try to gather a checklist of information on what the Green Communities program would like in return for the grant. | 2013-12-11 | Susan | 2013-12-20 | Closed | 1/9: Green Communities activity is on-going. We are waiting to see if the state will allow the addition of the library building to the town's list of eligible properties for the Greeen Community program. We should know mid-January what their decision is. 2/20/14 - Anne attended the meeting this evening, and the update is contained in the minutes of the Feb 20 meeting. | 2014-02-20
68 | Suggest a day next week to meet with Anne Mazar to discuss the Green Communities program grant. | 2013-12-11 | David E. | 2013-12-13 | Closed | 1/9: Abacus/Situ met with the Green Communities program representatives and the Mendon program coordinators on December 18th. | 2013-12-13
69 | Ask Fred Lapham of Shea Engineering if a site survey has been done at the location of the future Taft Public Library. | 2013-12-11 | Kevin | 2014-01-09 | Closed | 1/9: Kevin is still pursuing this. He will have an update at the next meeting. 2/20/14: Mary and David have been in contact with Fred Lapham and they will work with him on the need for a site survey, as one has not been done. | 2014-02-20
70 | Post the septic system plans to the library website. | 2013-12-11 | Andrew | 2013-12-13 | Closed | 1/9: Andrew posted the plans to the library website. | 2013-12-13
71 | Revisit the linear feet for shelving in the new Taft Public Library. | 2013-12-11 | Andrew | 2014-01-09 | Closed | 1/9: Andrew is reviewing with the MA Library Systems and will have an update at our next meeting. 2/20/14: Andrew updated the Committee on the current shelving at this meeting and the document is attached. | 2014-02-20
72 | Send pointer to original floor plans created from DRA to Abacus/Situ. | 2013-12-11 | Don | 2013-12-13 | Closed | 1/9: Don sent the pointer to all plans that are available on the website. | 2013-12-13
73 | Send soft-copy of all handouts given out at meeting to Don to attach to the minutes. | 2013-12-11 | Andrew | 2013-12-13 | Closed | 1/9: Andrew supplied Don with the handouts and Don attached them to the draft meeting minutes. | 2013-12-13
74 | Start process of investigating what's needed for a public water supply. Send info received so far from MASS DEP to Abacus/Situ. | 2013-12-11 | Joe | 2014-01-09 | Closed | 1/9: This item is on-going with Abacus taking the lead. 2/20/14: The Committee knows what is needed for a public water supply. Since the library does not anticipate having more than 25 patrons in the building at the same time for more than 60 days out of the year, a public water supply is not needed. | 2014-02-20
75 | Send link and explanation of what's contained in the Decision Action Log to Abacus/Situ. | 2013-12-11 | Don | 2013-12-13 | Closed | 1/9: Don sent link and explanation to Abacus/Situ after the last meeting. | 2013-12-13
76 | Send a draft of an RFP for Industrial Hygienist consultants to perform a hazardous material assessment of the former church to Mary/Building Committee so they can review it at their next meeting. | 2013-12-11 | David E. | 2014-01-09 | Closed | 1/9: Abacus is working on this. Mary will follow up with them on the status. 3/11/14: The Committee approved the use of Universal Environmental Consultants for the hazardous material inspection and design. | 2014-03-11
77 | Contact Town Counsel to determine who hires the Industrial Hygienist consultants. | 2013-12-11 | Joe | 2014-01-09 | Closed | 1/9: Joe will follow up with Town Counsel once we get the draft from Abacus. 3/11/14: The process we're following with allowing Abacus to research options and for the Building Committee to approve the selection for reimburseable expenses will continue. | 2014-03-11
78 | Take a look at the roof of the former church to understand how many layers of material exist. | 2013-12-11 | Jay | 2014-01-06 | Closed | 1/9: There are two layers of shingles on the roof, the most recent layer within the last ten years. | 2014-01-09
79 | Add linear footage and color code by collection type to the shelving on the next revision of the drawings. | 2014-02-06 | David E. | 2014-02-20 | Closed | 2/20/2014: David provided an updated drawing with color coding of the type of collections for each type of shelving. | 2014-02-20
80 | Provide a cost of replacing the stairs from the main level to the lower level with code compliant ones. | 2014-02-06 | David E. | 2014-03-06 | Closed | 3/11/14: The Committee decided to replace the stairs as part of selecting a specific design from Abacus. | 2014-03-11
84 | Write a letter stating that we don’t anticipate that the occupancy of the new Taft Public Library will exceed 25 people more than 60 days per year. | 2014-02-06 | Andrew | 2014-03-06 | Closed | 3/4/2014: Andrew has all the information regarding usage of the library, but the group is holding off on a letter until it knows more about what is needed for a Public Water Supply. 3/11/14: The Public Water Supply issue is much more complex than originally thought so this letter won't be needed. | 2014-03-11
86 | Ask Shea Engineering for quote for a site survey. | 2014-02-06 | David E. | 2014-03-06 | Closed | 3/4/2014: Abacus has a quote for a site survey. The Owner is responsible for a topographic survey and Abacus will use Shea for the complete survey. | 2014-03-04
87 | Look into obtaining a quote for testing for hazardous material. | 2014-02-06 | Mary/David E. | 2014-03-06 | Closed | 3/4/2014: Abacus has a quote for the testing. It will be reviewed by the Building Committee at the meeting on 3/11. 3/11/2014: The quote was reviewed and approved at the meeting on 3/11/14. | 2014-03-11
88 | Obtain a copy of the Mendon Zoning By-Laws and provide them to Abacus/Situ. | 2014-02-06 | Mary | 2014-03-06 | Closed | 2/20/2014: Mary supplied the Zoning By-Laws to Abacus/Situ. | 2014-02-20
89 | Arrange a meeting with BVT to begin discussions on potential support of the project, like installation of insulation/siding panels, construction of furniture, etc. | 2014-02-06 | Mary | 2014-03-06 | Closed | 3/20/2014: Mary has left messages for Tom Belland at BVT and is awaiting his reply. 3/26/2014: Mary met with Tom Belland and now has a better understanding of what type of work the students can assist with. They were recently removed from the Upton work due to concerns from contractor insurers. It was suggested that we use BVT now for demo work prior to bringing a GC on board. Work could also be done at the school and brought in. Perhaps the students could build some items for the new library. | 2014-03-26
90 | Drop the signed copies of the contract with Diane Willoughby on Monday so that the Board of Selectmen can sign them. | 2014-02-06 | Andrew | 2014-02-10 | Closed | 2/20/2014: Andrew dropped off the signed copies with Diane at the BOS office. | 2014-02-20
91 | Let Abacus know that they will need to start putting together a list of things that could be Green Communities grant eligible along with the specifications, costs and ROI. | 2014-02-20 | Mary | 2014-03-06 | Closed | 3/20/2014: The Committee agreed to pursue high efficiency air source heat pumps for the HVAC system and to apply for a Green Communities Grant for a better system than the Committee could originally afford. 3/26/2014: Mary has been working with David Eisen on finalizing the insulation decisions so that the cost estimates for the HVAC system can be completed. Work should be completed in time for the grant application. | 2014-03-26
92 | Update the Committee on whether the library is eligible for the Grant Communities Grant program. | 2014-02-20 | Anne M. | 2014-03-06 | Closed | 3/4/2014: Anne informed the committee that the library is eligible, but the town needs to close out existing projects before being able to apply for more. She'll know more about this by 3/13/2014. 3/20/14: Anne informed the Committee that $130K is available for the library via the Green Communities Grant Program. The application deadline is April 18th and Anne will help with the narrative. | 2014-03-20
93 | Provide oil consumption information from former church to Sergio/David | 2014-03-04 | Don | 2014-03-11 | Closed | 3/11/2014: Don forwarded the oil consumption information to David and Sergio. | 2014-03-11
94 | Follow up with Board of Selectmen to validate that process being used is appropriate for handling owner expenses. | 2014-03-04 | Joe/Don | 2014-03-20 | Closed | 3/11/2014: The process being used is working out well for the BOS's office and will continue. | 2014-03-11
95 | Contact the Water Commissioners to find out who the town uses for its public water supply management and testing. | 2014-03-04 | Joe/Don | 2014-03-20 | Closed | 3/11/2014: The Water Commission uses Tim Watson for the testing and maintenance of the town's public water supplies. Future engagement with that board will need to take place. | 2014-03-11
96 | Contact the Town Clerk to inquire about whether a public meeting can be held in a building without a public water supply. | 2014-03-11 | Joe | 2014-03-20 | Closed | 3/20/2014: Joe received an update from the Mass. DEP via the Mendon Board of Health that stated that "changing the status of the meeting rooms to public use is the trigger for public water system determination". Given this, the Committee will continue to pursue this with Abacus and Fred Lapham of Shea Engineering. | 2014-03-20
97 | Check to see if an electric backup is required for air source heat pumps. | 2014-03-11 | Mary/David E. | 2014-03-20 | Closed | 3/20/2014: Abacus’ engineering consultant Sergio Siani stated that “the heat pumps would be sized so that they alone can provide the required heat. We have a number of these installed in projects that heated the buildings during this past cold winter without needing supplementary heating.” | 2014-03-20
99 | What are the startup costs of the two different efficiency versions of the air source heat pumps? | 2014-03-11 | Mary/David E. | 2014-03-20 | Closed | 3/20/2014: The comparisons of all HVAC options were updated and reviewed and the high efficiency air source heat pump was chosen as the one to be pursued. | 2014-03-20
100 | Update the comparisons for startup and operating costs for the top three options and clearly show with and without A/C so we can compare apples to apples. | 2014-03-11 | Mary/David E. | 2014-03-20 | Closed | 3/20/2014: The comparisons of all HVAC options were updated and reviewed and the high efficiency air source heat pump was chosen as the one to be pursued. | 2014-03-20
101 | Work with Bill and Anne to clarify the role of the Green Communities Grant Coordinator (Bill's role) should a grant be received. | 2014-03-20 | Don | 2014-03-26 | Closed | 3/26/2014: Don exchanged emails with Anne who described the role of Bill which is to make the projects run smoothly and coordinate details and logistics of the GC projects. He also uploads the energy data in to the MassEnergyInsight computer program. | 2014-03-26
102 | Investigate options for replacing the single pane windows. | 2014-03-20 | Mary | 2014-04-08 | Closed | 3/26/2014: Mary had Pace Glass look at the windows and they recommended that we start over and not try to retrofit the existing windows. Two other firms said the same thing. Mary has Milford Glass coming out to look as well. 4/8/2014 Mary stated that DVW will be visiting the church next week. They are currently retrofitting the windows at the Milford Town Hall. 4/22/14: Nothing new to report as Mary was not in attendance. 5/6/14: Mary had the final firm look at the windows and they confirmed that the windows will need to be replaced. | 2014-05-06
104 | Put together a budget summary for review at all future meetings. | 2014-03-20 | Don/Joe | 2014-03-26 | Closed | 3/26/2014: Mary and Paul have supplied example budget tracking documents for Joe and Don to use. They will have one for review a the April 8 meeting. 4/8/2014: Don shared a sample budget tracking sheet with the Committee and it was well received. Paul suggested adding a column on the summary page to specify the awarded amount for each budgeted item. Don agreed to do this. 4/22/2014: The budget will be reviewed at all future meetings.
105 | Ask Abacus when a 30% review will be ready along with a cost estimate. | 2014-03-20 | Mary | 2014-03-26 | Closed | 3/26/2014: The 30% review and cost estimate were being held up by the site plan and HVAC work. Now that those are being completed, Abacus should be able to close this item soon. They are prioritizing the HVAC and insulation work now, as it will be needed for the Green Communities Grant application. 4/8/2014: The 30% review and cost estimate are still awaiting the site plan to be completed. 4/22/2014: Abacus expects to have a review and cost estimate ready for our next meeting on May 6. 5/6/2014: 30% design and initial cost estimate was provided for our meeting on May 6. A detailed review will take place with the architect on May 12. | 2014-05-06
108 | Check into the possibility of getting dumpsters supplied to support the BVT work. | 2014-04-08 | Paul | 2014-04-22 | Closed | 4/22/2014: Paul was able to get dumpsters for the boiler demo work. Thanks Paul!
109 | Check on the availability of a licensed engineer to perform the analysis of the soil conditions at the future location of the elevator. | 2014-04-08 | Dan | 2014-04-22 | Closed | 4/22/2014: Dan was able to get a structural engineer to certify the soil analysis at the site of the future elevator. Unfortunately, Abacus' structural engineer prefers to have borings dug at the site to better guarantee the conditions of the soil. Therefore, Dan's engineer will not be used.
112 | Share the results of the Geo Tech Borings and test pits with the Committee when complete. | 2014-05-06 | Mary | 2014-05-27 | Closed | 5/12/22: The Geo tech report came back favorable with regards to soil conditions for the future elevator, but ground water issues were discovered. There may be a need for a sump pump to be installed at the bottom of the elevator pit. 5/22/14: During the work by Yankee Engineering with the geo tech borings, it was discovered that there was no footing under the foundation in a location where one should have been located according to the as-built drawings for the former church. As a result, Mary obtained a quote from Yankee Engineering to dig additional test pits to determine if other footings exist or if none are present. The Committee will decide upon next steps at their next meeting. | 2014-05-22
113 | Send David Eisen a list of the open items on the Decision Action Log ahead of the meeting on Monday, May 12. | 2014-05-06 | Don | 2014-05-12 | Closed | 5/12/14: Don sent the list to David the morning following the May 6 meeting. | 2014-05-12
114 | Check if the Worcester County Sherriff’s department offers services to perform demo work for communities within Worcester County. | 2014-05-06 | Mary | 2014-05-12 | Closed | 5/12/14: Mary checked with the Worcester County Sherriff's office and indeed they do perfom demo work for communities. Joe Cronin agreed to work with the Mendon Board of Selectmen's office to draft a letter requesting support. | 2014-05-12
120 | Work with the Town to draft a letter to the Worcester County Sherriff’s office to inquire about obtaining volunteers to perform demolition work at the work site. | 2014-05-12 | Joe | 2014-06-02 | Closed | 5/22/2014: Joe worked with the Town and a letter has been drafted and sent to the Worcester County Sherriff's office requesting support for demo work. | 2014-05-22

## Potential Future Action Items
Renovation of Saint Michael's Church to the Taft Public Library
Potential Future Action Items: | Comments
Septic System reqt's for a public library
Lead Paint
Asbestos
Rectory & Church Heating System
Rectory & Church Electrical System
Well, well pump, water volume, need for public water supply | Need to understand what testing is needed and any other requirements for water supply for the new building.
Alternative Energy Methodology | Paul mentioned that Bob Russell of National Grid offered to make suggestions for energy efficiency improvements when we get to the design phase of the project.
Utility Rebates/Incentives
Sprinklers
Water seepage | Please refer to June 17, 2013 Bulding Committee memo from Joe Cronin.
Parking Lot Lighting
Outdoor Mounted Equipment | Provide sound proofing, fencing, etc.
Snow Removal (steps and walk) for winter of 2013-2014

## Donation List
Renovation of Saint Michael's Church to the Taft Public Library
Donations for the Project | [5 empty] | Rev. 5
2014-04-22
Item # | Item Description | Donated By | Date | Value of Donation | Written Acknowledgement | Comments
1 | Home of Taft Public Library Sign | Joe Cronin | 2013-03-25 | 44 |  | Sign materials paid for by Joe Cronin with labor supplied by BVT.
2 | Adult Section Library Shelving | Lawney Tinio/Consigli Corporation | 2013-04-18 | 8750 |  | Book shelving was secured By Lawney Tinio from the UMass Dartmouth Library Renovation Project being performed by Consigli Construction. Unfortunately the shelving was not useful to the project.
3 | Donation of brokerage commission | Judy Leonelli, Millennium Realty | 2013-06-04 | 3000 | Yes, by Friends of TPL | Ms. Leonelli performed brokerage services for Town of Mendon for purchase of St. Michael's Church and generously donated her full commission back to the project.
4 | Volunteer to mow lawn at new site | Jay Washburn and son | 2013-05-27 | 50 |  | Jay and his son cut the lawn as the Parks Department can’t pick up this work until July.
5 | Volunteer to mow lawn at new site | Mike Watson | 6/8/2013 & 6/16/2013 | 100 |  | Mike cut the lawn as the Parks Department can’t pick up this work until July.
6 | $10,000 matching grant | Kevin Rudden | 2013-10-08 | 10000 | Yes, by Taft Library Trustees | Kevin is providing a $10,000 matching grant to the Taft Library Building project from their parents' estate in their memory. The grant will match donations to the project dollar for dollar up to $10,000.
8 | Scrap Metal and Refuse Dumpsters | Paul Fitzgerald | 2014-04-14 | 500 |  | Paul obtained dumpsters for the scrap metal from the boiler demo work performed by BVT students.
9 | Coffee, Donuts and Hot Cocoa | Mary Bulso and Joe Cronin | 2014-04-17 | 50 |  | Coffee, Donuts and Hot Cocoa provided to BVT students during their boiler demo work.
10 | Public Water Supply Support | Fred Lapham |  |  |  | Placeholder --- will update with more information soon
11
12
13
14
15
16
17
18
19
20